## Summary
ERP_RMI_SOFULL - Execution Plan Summary
Option | Total Tasks | Total Estimasi (jam) | Notes
Option A | 12 | 85 | Aman, incremental, rollback per file/folder.
Option B | 6 | 54 | Cepat, batch via automation tool; perlu regression ekstra.

## Option_A
Ready-to-Execute Task List - Option A (Incremental / Per-Module)
ERP | ERP_RMI_SOFULL
Generated | 2026-01-07 22:49:36
ID | Workstream | Task | Detail | Deliverable | PIC | Estimasi (jam) | Urutan | Dependency | Rollback | Verifikasi
A01 | Foundation | Lock baseline RBAC mapping (Dept+Level → Permission) + enforcement map per file | Freeze baseline mapping (Lampiran B) as source-of-truth. Create/validate enforcement mapping URL/File → Permission for PURCHASES, MASTER, KPI, DASHBOARD, TOOLS. Decide deny-by-default rules & admin bypass. | Baseline mapping doc (xlsx tab) + enforcement_map.php (or MD) ready to apply; sign-off Owner/ITC. | Dev + Owner | 4 | 1 | RBAC Center & master_departements already seeded | N/A (planning only) | Review session with Owner: sample 10 URLs vs expected permission.
A02 | Purchases | Create purchases/_purchases_bootstrap.php (single gate) + helpers | Add module bootstrap: require _shared/bootstrap.php; require_login(); provide purchases_pdo(); purchases_rbac_require(); purchases_require_dept_or_admin(); JSON-safe deny for API endpoints; centralize common includes. | New file purchases/_purchases_bootstrap.php + README snippet; lint OK. | Dev | 3 | 2 | _shared/bootstrap.php + helpers installed | Remove bootstrap file; revert requires. | php -l purchases/_purchases_bootstrap.php; open purchases/purchases_dashboard.php after temporary include.
A03 | Purchases | Enforce server-side guard on Purchases entrypoints (23 files) - phase 1 | Add 2 lines on top of each purchases/*.php: require _purchases_bootstrap.php + purchases_rbac_require(per-file perm). Start with most sensitive: purchases_payment_ap.php, purchases_invoice_ap*.php, purchases_import_control_*.php, purchases_forwarder_*.php, purchases_ceisa_pib*.php. | Direct URL as unauthorized role returns 302 login or 403; no blank pages. Updated files committed/backed up. | Dev | 10 | 3 | A02 | Restore per-file from backup folder (_backup/...). | UAT 10 cases: staff SALES denied AP pages; FIN staff allowed edit; FIN manager allowed approve; ACT allowed CEISA.
A04 | Purchases | Upload hardening for 9 Purchases upload pages | For each file with $_FILES: enforce rmi_safe_filename(); use rmi_safe_code() for folder; allowlist ext (pdf/jpg/png/xlsx/csv); max size (e.g., 50MB); realpath prefix check; reject invalid. Ensure delete actions validate object-level authorization. | No path traversal; invalid ext/size rejected; uploads stored under /uploads/purchases/<safe_code>/; audit entries (if enabled). | Dev | 8 | 4 | A03 (guards first) | Restore affected files + remove new upload dirs created during test. | Try upload filename '../evil.php' (should sanitize + reject ext). Upload pdf OK. Delete doc denied for unauthorized dept.
A05 | Purchases | CSRF for Purchases critical POST actions | Add CSRF token to forms: DP/Final payment, approve actions, upload/delete docs. Verify token on POST; on fail return 403 with message. Backward-compat: allow turning off via config flag for emergency. | CSRF token generated per session; POST without token denied; no UX break. | Dev | 6 | 5 | A04 | Disable CSRF via config flag; revert form changes if needed. | POST replay without token denied; valid token passes; multi-tab works.
A06 | Master | Master upload hardening (11 pages) + object-level auth for docs | Identify master pages with uploads (manufactures docs, product media, etc). Apply rmi_safe_filename/safe_code + allowlist + size + realpath. Enforce MASTER.DOC_UPLOAD/DELETE permissions and ownership rules (dept PQP/SCM + admin bypass). | Uploads safe; delete guarded; unauthorized access denied server-side. | Dev | 12 | 6 | A01 baseline mapping | Restore files from backup; keep uploaded files but lock access. | Staff non-owner dept cannot upload/delete; admin can; view works.
A07 | Master | Standardize output escaping (rmi_h) + fix unguarded h() redeclare | In master module files flagged 'h() unguarded', wrap legacy h() defs with function_exists guard; replace risky echoes with rmi_h(). Prioritize pages exposed to many roles. | No 'Cannot redeclare h()'; reduced XSS surface; pages render same. | Dev | 8 | 7 | M2 helpers installed | Restore files from backup. | Run php -l; spot test with special chars in input (e.g., <script>) renders escaped.
A08 | KPI | KPI access control enforcement (VIEW/EDIT/ADMIN) + guard endpoints | Add require_login + rbac_require: KPI.VIEW for manager+/admin; KPI.EDIT/KPI.ADMIN for HRL/admin. Ensure JSON endpoints deny-by-default; hide menu remains UX only. | Staff cannot access KPI pages or JSON; managers can view; HRL/admin can edit. | Dev | 6 | 8 | A01 baseline mapping | Restore KPI files; temporarily restrict via .htaccess if needed. | Test 3 roles: staff denied, manager view ok, HRL edit ok.
A09 | Dashboards | Dashboard server-side RBAC + data scope (dept/office) | Add require_login + rbac_require for each dashboard page. Ensure queries scope by office_code/role where applicable (avoid data leakage). Ensure cache key includes user role/dept (if caching). | No dashboard accessible without permission; owner/exec only for exec view. | Dev | 6 | 9 | A01 baseline mapping | Restore dashboard files; disable dashboard links temporarily. | Direct URL tests across roles; check no cross-office data leakage.
A10 | Tools/Security | Lock down TOOLS.RUN pages (fin_gl_auto.php, stock_update_from_gr.php) | Make tools CLI-only OR admin-only with explicit deny for web. Add guard: if php_sapi_name()!='cli' then require admin+csrf. Log executions with request_id and username. | Tools cannot be triggered by regular users; only admin/cli. | Dev + DevOps | 4 | 10 | RBAC core present | Restore old tool files; keep tools inaccessible via web (rename). | Attempt open via browser as staff → 403; run via CLI works (if allowed).
A11 | Audit/Observability | Implement structured audit logging for critical events (no new table by default) | Add audit_log() helper writing JSON lines to /logs/audit_YYYYMMDD.log with masking. Events: RBAC change, AP payment, PO approve, upload/delete docs, stock adjustment. Optionally switch to DB table if compliance requires. | Audit file logs created; events recorded consistently. | Dev | 6 | 11 | M2 helpers; writable logs folder | Disable audit logging flag; remove log writer; keep existing logs archived. | Perform 3 actions and confirm log lines written with username/role/entity.
A12 | UAT/Go-Live | UAT matrix + anti-privilege escalation tests (horizontal & vertical) | Run test matrix per dept (WQS/FIN/SCM/PQP/SALES/HRL/ACT). Include direct URL tests, API tests, upload negative tests, approval flow tests. Capture evidence screenshots and sign-off. | UAT checklist completed + sign-off; issues logged with severity & fix plan. | Ops + Dev | 12 | 12 | A03-A11 completed | If SEV1 found, rollback affected module files and re-test. | All critical tests pass; no unauthorized access; no upload bypass.

## Option_B
Ready-to-Execute Task List - Option B (Batch / Automation)
ERP | ERP_RMI_SOFULL
Generated | 2026-01-07 22:49:36
ID | Workstream | Task | Detail | Deliverable | PIC | Estimasi (jam) | Urutan | Dependency | Rollback | Verifikasi
B01 | Automation | Build auto-inject tool for RBAC enforcement + upload hardening | Create CLI tool (tools/rbac_enforce_apply.php) that: reads enforcement mapping, injects bootstrap+rbac_require lines into entrypoints, adds safe_filename/safe_code patterns for upload, supports --dry-run, creates timestamped backup. | Tool runs on dev; produces change report; backups created. | Dev | 8 | 1 | Baseline mapping A01 | Tool always creates backup; restore from backup folder. | Dry-run matches expected diff; apply then php -l sample files.
B02 | Automation | Prepare enforcement mapping file (machine-readable) for Purchases/Master/KPI/Dashboards/Tools | Create tools/enforcement_map.json (or php array) mapping file→permission and file→dept fallback. Include exceptions (public assets, include-only files). | enforcement_map ready; reviewed and approved. | Dev + Owner | 4 | 2 | B01 | N/A | Spot-check 20 files mapping correctness.
B03 | Batch Apply | Run tool on purchases/ (batch) + hotfix exceptions | Execute tool apply for purchases. Fix any parse errors or unique file structures manually. Ensure 9 upload pages hardened. | Purchases module fully guarded & uploads hardened in one batch. | Dev | 10 | 3 | B02 | Restore purchases from backup folder. | Direct URL deny tests + payment flow smoke test.
B04 | Batch Apply | Run tool on master/ and sales/ (batch) + hotfix exceptions | Apply tool for master and sales modules. Ensure no h() redeclare; add rmi_h replacements where pattern can do safely. Harden uploads. | Master/Sales guarded; upload hardening applied; minimal manual fixes. | Dev | 12 | 4 | B03 | Restore master/sales from backups. | Smoke test 15 URLs; upload negative tests.
B05 | Batch Apply | Run tool on kpi/ dashboards/ tools/ (batch) + deny-by-default | Apply tool; enforce KPI view/edit; dashboards view perms; tools cli-only/admin. Ensure API endpoints return 401/403 properly. | Sensitive read endpoints closed; dashboards scoped. | Dev | 6 | 5 | B04 | Restore folders from backups. | Role-based access tests; attempt bypass via direct URL.
B06 | UAT/Go-Live | Full regression + UAT after batch | Run full regression checklist >=20 cases: login redirect, deny-by-default, approve gates, upload safety, API read safety, CSRF (if enabled). | Regression report + sign-off. | Ops + Dev | 14 | 6 | B03-B05 | Rollback whole module folders if critical failures. | All SEV1/SEV2 resolved; audit scan improved significantly.